## roadmap-9b6fa81484dd33cda00c592
Feature | Type | Feature Detail | Tentative Timeline | Size | Skill Needed
GenesisX | Generator | Rebrand Genesis to Genesis X | 2022 Q3 | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | Express based Mock API service and Generators for React and Angular SPA | 2022 Q3 | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | Howathon support | 2022 Q3 | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | To integrate Lighthouse plugin and enable in Jenkins pipeline | 2022 Q4 | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | Containerization for Kubernetes and Docker - To create Docker images for the GenesisX apps | 2022 Q4 | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | To get KT from David on TurboRepo workspace | 2022 Q4 | Medium | React, Typescript, Nodejs, Nx
Web Accessibility | Plugin | CI CD based web accessibliity plugin | 2023 Q1 | Medium | React
Universal React Merge to GenesisX | Accelerator |  | 2023 Q1 | Large | React
Performace Tool Integration | Plugin | Lighthouse or similar tool in CI / CD | Not Planned yet | Medium | React
Caching on GQL Layer | Feature | Redis , Varnish or any other cache | Not Planned yet | Medium | React
Algolia Search | Feature | Text based search for documentation | Not Planned yet | Large | React
Nest JS Generator | Generator | Generator for Nest JS | Not Planned yet | Large | React
Jade | Generator | Ecomm templating sample app | Not Planned yet | XLarge | React
Universal React various accelerators | Generator |  | Not Planned yet | Medium | React
Code Shaper | Generator | Moving all generators to codeshaper | Not Planned yet | XXL | React
GenesisX | 2022 Q3 | Git Hooks Plugin Testing and Verification | DONE | Large | React, Typescript, Nodejs, Nx
GenesisX | 2022 Q3 | Analysis of Refactoring or creating new generator for Mock server using open mocks | DONE | Large | React, Typescript, Nodejs, Nx
GenesisX | 2022 Q4 | Modify Interface of plugin to generate 4 Arch types @Jamal | Not Planned yet | Large | React, Typescript, Nodejs, Nx
GenesisX | Generator | Feedback | Not Planned yet | Large | React, Typescript, Nodejs, Nx
GenesisX | Generator | Merge universal React to GenesisX | Not Planned yet | Large | React, Typescript, Nodejs, Nx
GenesisX | Generator | GenesisX-Upgrade NX to v14 | DONE | Large | React, Typescript, Nodejs, Nx
GenesisX | Generator | For Vanilla JS Application like jQuery | DONE | Large | React, Typescript, Nodejs, Nx
GenesisX | Generator | To create a new stage/pipeline to publish packages to npm | Not Planned yet | Large | React, Typescript, Nodejs, Nx
GenesisX | Generator | GenesisX-CI/CD | Not Planned yet | Large | React, Typescript, Nodejs, Nx
Initial setup for State management module | React Accelerator | Add/ Update template for 4 type of Archs - Micro app generator with Module Federation | Not Planned yet | Large | React
React Accelerator | Generator | Initial setup of the plugin @Sagar Arora | Not Planned yet | Large | React
GenesisX | Generator | Howathon support | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX-Upgrade NX to v14 | Generator | Testing and validation | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX-CI/CD | Generator | To create a new stage/pipeline to publish packages to npm | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX-CI/CD | Generator | To enable Automated Jenkins pipeline on commit to Master | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX-CI/CD | Generator | To fix the current Jenkins pipeline for all package builds | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | GenesisX-SuperGraph with Gateway | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
React Accelerator | React Accelerator | Add/Update template for State management - Smart Context | Not Planned yet | Medium | React
React Accelerator | React Accelerator | Define interface for State Management | Not Planned yet | Medium | React
React Accelerator | React Accelerator | Add/Update template for State management Redux Toolkit | Not Planned yet | Medium | React
React Accelerator | React Accelerator | Initial setup for State management module | Not Planned yet | Medium | React
React Accelerator | React Accelerator | Add/ Update template for 4 type of Archs - Micro app generator with Module Federation | Not Planned yet | Medium | React
React Accelerator | React Accelerator | Add/Update template for 4 type of Archs - Pure React Stitching Layer | Not Planned yet | Medium | React
React Accelerator | React Accelerator | Add/Update template Tor 4 type of Archs - Next.js SSG/SSR/ISR @Apoorva | Not Planned yet | Medium | React
React Accelerator | React Accelerator | Modify Interface of plugin to generate 4 Arch types @Jamal | Not Planned yet | Medium | React
GenesisX | Generator | To integrate Lighthouse plugin and enable in Jenkins pipeline | Not Planned yet | Medium | React
GenesisX | Generator | Containerization for Kubernetes and Docker - To create Docker images for the GenesisX apps | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | To get KT from David on TurboRepo workspace | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
Genesisx Accelerator | Generator | For Vanilla JS Application like jQuery | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | Implementation and Testing - Refactoring or creating new generator for Mock server using open mocks | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | Upgrade NX to v14: Merge to master | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | SuperGraph with Router | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | Github Workflow integration unavailable | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
React Accelerator - Design System Integration Plugin | React Accelerator | Choose Library - NextUI | Not Planned yet | Medium | React
React Accelerator - Design System Integration Plugin | React Accelerator | Choose Library - ChakraUI | Not Planned yet | Medium | React
React Accelerator - Design System Integration Plugin | React Accelerator | Choose Library - MaterialUI | Not Planned yet | Medium | React
React Accelerator - Design System Integration Plugin | React Accelerator | Interface definition | Not Planned yet | Medium | React
React Accelerator - Design System Integration Plugin | React Accelerator | Initial setup | Not Planned yet | Medium | React
React Accelerator - Component Generator Plugin | React Accelerator | Enhance definition of custom templates | Not Planned yet | Medium | React
React Accelerator - Component Generator Plugin | React Accelerator | Enhance to make it work with NX | Not Planned yet | Medium | React
React Accelerator - Component Generator Plugin | React Accelerator | Migrate existing capabilities | Not Planned yet | Medium | React
React Accelerator - Component Generator Plugin | React Accelerator | Interface definition | Not Planned yet | Medium | React
React Accelerator - Component Generator Plugin | React Accelerator | Initial setup | Not Planned yet | Medium | React
Genesis Implementation and Testing | Generator | Integrating AXE core in Jenkins pipeline for Genesis for A11Y | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | POC on integration of search in Docusaurus | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | Add generator for Nest.js | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | Explore Varnish Cache | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | Explore Redis caching strategy | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | Explore caching on Graphql layer | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX | Generator | AAD B2C Accelerator - To explore Azure authentication / Azure AD | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
Feedback | Generator | Selenium based Testing framework support - Integrate TestX with GenesisX | Not Planned yet | Medium | React
GenesisX | Generator | Add generator for Algolia Search | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
GenesisX Analysis | Generator | Integrating AXE core in Jenkins pipeline for GenesisX for A11Y | Not Planned yet | Medium | React, Typescript, Nodejs, Nx
React Accelerator - Component Generator Plugin | React Accelerator | Initial setup of the plugin @Sagar Arora | React Accelerator | Medium | React